## Sheet1
ES Culham |  |  | Updated | 2016-05-19
Arrangements for Closure of School on 31/08/2017
Comments
A. Administrative
| On site storage facilities after 31/08/2017 |  |  |  | Contact Europa School
| Storage of pupils files (how long to be kept) |  |  |  | Storage at Bergen or Mol
| Staff personal files (how long to be kept) |  |  |  | At least 10 years
| Person to be retained to deal with administrative matters after 31/08/2017 |  |  |  | To be decided
| Minutes of Admin. Board meetings etc. |  |  |  | Store at BSG
| Cancelling X number plates for seconded staff |  |  |  | To be done before 31/08/2017
| Cancelling school registration with UK Foreign Office |  |  |  | To be done before 31/08/2017
| Collection of keys from staff |  |  |  | To be done before 31/08/2017
| Shut down of ICT systems and email accounts |  |  |  | Liaise with Roland Pirnay
| Close down the website - information redirected? |  |  |  | To be done by ESC
| Dealing with mail received after 31/08/2017 |  |  |  | Person to be decided
| Setting up contact email address after 31/08/2017 |  |  |  | Liaise with Roland Pirnay
| Requests from staff for employment references after 31/08/2017 |  |  |  | Try to issue references before 31/08/2017.BSG after 31/08/2017
| SMS leaving date for pupils transferring to ESUK - 07/07/2017 or 31/08/2017 or leave it open |  |  |  | 2017-08-31
| Pupils are withdrawn from SMS on the last day of their schooling. What about summer 2017? Will that be the last day of school or 31.08.17? |  |  |  | 2017-08-31
| Official certificate that ES Culham has closed |  |  |  | To be drawn up by BoG
| ADM server - to send it to Brussels? When? |  |  |  | Liaise with Roland Pirnay
| Closing down email accounts for staff - autoresponse about school closure after 31.08.2017 |  |  |  | To be done by ESC (staff to be notified in advance)
Keep email accounts for staff transferring to other ES's
Keep email accounts for Soekov, Holcombe and Turrell
| Where would the data and hardware go? |  |  |  | Liaise with Roland Pirnay
| Staff files on the computers - should we backup and copy them ? Whose expense? |  |  |  | Hard disks to be removed from admin PC's and other PC's
The data in the user areas - again to be copied or backup made?
Gaignage
E.g. a teacher in another ES is finishing his/her 9th year in 2017. Our teacher is ready for transfer. What about the "receiving" school asking for the 10th year of their own teacher. Does Gaignage trump the 10th year? Options?
|  | Can Gaignage be deferred for a year? |  |  | No
The staff will write a priority list of the schools they would like to go to. Does the preferred school have to take the person?
Arrangements for transfer for seconded and locally recruited staff.
|  | Are we talking about transfer or a new contract for the locally recruited staff? |  |  | New contract at destination school
|  | Retention of the former salary scale for locally recruited staff (teachers and admin. staff) |  |  | Old statute staff retain old statute salary scale. Admin staff go on scale of destination school.
LR and PAS staff have to apply for posts in other ES's under open competition. If there are
two equal candidates short listed then the ESC candidate gets the job.
| Students |  | in case they would like to be transferred to another European School are they going to get priority over other admissions?
| Admin computers |  |  |  | Remove hard disks and label with name
| Admin staff to be retained after 31/08/2017 |  |  |  | Contracts to be set up
B. Financial | Persons to be retained to deal with financial matters after 31/08/2017
Financial matters after 31/08/2017:
Payment of invoices
Collection of any unpaid school fees
Access to SAP, SMS and PERSEE
|  | Seconded staff: |  | Resettlement and departure allowances | Try to pay before 31/12/2017
|  |  |  | Removal expenses | Try to pay before 31/12/2017
|  |  |  | Submission of national tax documents | To be managed by R Holcombe
|  |  |  | National salary slips submitted after 31/08/2017 | To be managed by R Holcombe
|  |  |  | BSG to deal quickly with tax calculations | Noted by Julio
|  |  |  | Reimbusement of part of installation allowance | Andreas Beckmann to check
for staff with less than 5 years service
|  | SAGE payroll |  |  | ESC to close down payroll
|  | Closure of accounts for 2017 |  |  | To be done by R Holcombe
Banking arrangements
|  | Salary increase from 01/07/2017 (paid in 2018) |  |  | To include in budget of Bergen or Mol
|  | Appointment of authorising officers and accounting officers |  |  | To be decided
| Termination of contracts of employment for locally recruited staff |  |  |  | To be done by ESC
| Issue of P45's to LR staff (teaching and AAS) |  |  |  | To be done by ESC
| Settlement Agreement payments |  |  |  | To be done by ESC
| Termination of contracts for goods and services |  |  |  | To be done before 31/08/2017
| Termination of pension schemes |  |  |  | To be done before 31/08/2017
| Termination of Joint Sickness Insurance Scheme ( seconded staff) |  |  |  | To be done before 31/08/2017
6 months extension if can't get cover in home country
| Termination of Category 2 agreements |  |  |  | Notice to be given in January 2017
| Storage of salary files and records |  |  |  | To be decided
| Storage of accounting records |  |  |  | To be decided
| Disposal of old salary and accounting records (accounting records to be kept for |  |  |  | Work in progress
5 years ?)
| Counselling available in case of stress - pay for a certain number of hours (6?) |  |  |  | Check local law
Derogation concerning the number of teaching hours for seconded staff ( if needed)
| Relocation allowance for locally recruited staff transferring to other European Schools |  |  |  | Removal expenses paid for LR teachers (Art. 37 of Statute)
No decision yet for PAS
| Admin computers after 31/08/2017 |  |  |  | RH and MT can have VPN vonnection at home
C. Buildings and Equipment | Disposal of unwanted furniture and equipment
Hand over keys to Europa School
| Disposal of unwanted files and papers |  |  |  | Confidential papers to be shredded
D. Pedagogical | Transfer of files and data for pupils moving over to Europa School |  |  |  | Not to be done. Europa to set up files from scratch.
Storing of Bac scripts and artwork
Disposal of unwanted materials and equipment in classrooms
| Library - cancel magazine subscriptions |  |  |  | To be done before 31/08/2017
UCAS references - after the closure. Who will do that? Payments?
| Duplicates of BAC certificates. Who will sign after 31.08.2017 |  |  |  | Director of Bergen or Mol
Storage of examination papers of last 3 years
| The art BAC papers - could we give those back to students? |  |  |  | Must be kept for 3 years
My docs/Closure of ES Culham - Arrangements 19-05-2016

## Sheet1 (2)
2017-03-D-36-en-1-ANNEX-I
ES Culham | Updated | 2017-03-28 | NB! Colour code: beige - ES Culham only; no need for the intervention from OSGES so far; blue - task completed
Note: All names have been removed from this document to ensure confidentiality
Arrangements for Closure of School on 31/08/2017 |  |  | Comments | Responsible/ contact person | Where | When | Additional remarks
HR related issues
1. Storage of staff files
Staff personal files (seconded) |  |  | To be kept in OSGES for those who have finished in the system. Those transferring to another ES , their files should be sent to that particular school . There is no procedure about the transfer of files. | XXX | OSGES | To be transported in July 2017 | OSGES to clarify procedure for transferring of personal files - In case of transferring teachers to other ES - who gets original? Who gets copy?; Discussed with XXX. Files will be kept in OSGES
Staff personal files (locally recruited) |  |  | To be kept 6 years in full after the end of the contract and at least 120 years. The files of the locally recruited teachers probably cannot be transferred before 31/08/2017 because of TUPE? Depending on the signing of settelement agreements, might be possible in the middle of July. To be kept in OSGES | XXX | OSGES | XXX-most probably cannot be transported before August - please see comment | OSGES to clarify procedure for transferring of personal files - In case of transferring teachers to other ES - who gets original? Who gets copy?; Discussed with XXX. Files will be kept in OSGES
OSGES will be responsible for certifications requested by former staff members |  |  |  | XXX | OSGES | After 31/08/2017
Staff references after the closure |  |  |  | XXX | OSGES | After 31/08/2017 | Generic references are being produced by ESC. They will be printed and placed in personal files.
2. Working conditions for Bursar and Accountant after 31/08/2017
Bursar to work from home, the same for Accountant |  |  | Consult XXX and XXX | XXX | ES Culham/ OSGES
Amended contract to be drafted for Bursar |  |  | to the end of May 2018 | XXX | OSGES | May/June 2017 | We need to sign an amendment to the two contracts: the two people will work for the OSGES, but from home. Duration of contract is fixed. Legal side to be checked with HR Unit - to be locally recruited- which country?
Amended contract to be drafted for Accountant |  |  |  | XXX | OSGES | May/June 2017
3. Tasks for Bursar from 01.09.17 - 31.12.17
•DSG appointed as Authorising officer from 01.09.2017 , initiator – Accountant , verificator - Bursar; •the closure of accounts 2017; •From September 2017 – Bursar will be the accounting officer, the authorising officer –Deputy Secretary General; • For 2018 Bursar will be the initiator; verificator and authorizing officer -DSG. • Budget for 2018 to be prepared by OSGES together with Bursar Part of the budget of the OSGES Bursar – full time salary up to the end of 2017; 2018 – to be confirmed Bursar and Accountant on the OSGES paylist from 01 September 2017 |  |  | List of tasks submitted to Budgetary Committee | XXX | ES Culham/ OSGES | After 31/08/2017 | Proposal to extend contract also from 1/1/2018 to 31/5/2018 for Bursar and Accountant on part-time (50%).
4. Support for staff members - information on Gaignage to be circulated to inspectors and other schools. |  |  | To be done at directors' meeting Transfers for XXX, XXX andXXX - members of seconded staff - to be clarified. | XXX | OSGES | October 2016 | DONE
4.A.Seconded members of staff
Requirement to reimburse part of installation / resettlement allowance for staff with less than five years’ service |  |  | Opinion of Budgetary Committee requested | XXX | OSGES | 2016-11-01 | DONE
4.B. Locally recruited teaching staff
Arrangements for termination of contracts. Cdc could opt to claim "TUPE" rights |  |  | Local employment law to be followed; Unlikely to be TUPE transfers |  | ES Culham | Work in progress | Consultation with the local law company in progress
CdC can apply for vacancies in other European Schools and will be given priority ‘other things being equal' |  |  | Not a transfer situation; contracts with ES Culham will be terminated with the closure of the school and settlement agreement signed and paid to waive TUPE rights | XXX | ES Culham/ OSGES | Dec 2016 - the available posts were published; CdCs will be interviewed by the relevant Director to decide whether the candidate meets the requirements of the receiving school | Work in progress- limited interest from Type I schools so far
CdC will receive removal costs in accordance with Article 37 of the Service regulations |  |  |  | XXX | Destination school | After 31/08/2017 | Work in progress
Arrangements for applying to another European School for CdCs |  |  | CdC will receive a new contract, but will be entitled to the salary annex they belonged to before (example: CdC recruited in Culham before 1 September 2011 will be entitled to the salary scale of CdC recruited before 1 September 2011 applicable in the ‘receiving’ school) | XXX | OSGES | December 2016- July 2017 | DONE
4.C AAS
AAS applying for the same grade in another school will be given priority subject to the requirements of the national legislation; a publication of the post would not be necessary; successful candidates will keep their same step on the same salary scale, but no other acquired rights would be maintained (see decision of the BoG of 12, 13 and 14 April 2011 – doc. 2011-04-D-7-en-3). | [5 empty] | Candidates interviewed by the Director who decides whether the applicant meets the criteria set by the receiving school. | There seems to be only one member of AAS staff interested. But possibly not interested to move to another country. Continue with the process
AAS applying for a different grade shall apply like other candidates. Other things being equal and subject to the requirements of national legislation they will get priority (see decision of the BoG of 12, 13 and 14 April 2011 – doc. 2011-04-D-7-en-3).
Existing legal basis for payment of removal costs for AAS ( 3people) if accepting a post in another European School. |  |  | Doc 2016-10-D-21-en-2 ANNEX "Financial Consequences of the Proposals -Progress Report- Phasing -out of the European School Culham. Ceiling on removal costs - €3,000 | XXX | ES Culham/ OSGES | Approved by the BoG in December 2016 | DONE
Procedure for locally recruited administrative staff to apply to other European schools |  |  | CV and a letter of expressing interest must be provided by the AAS staff - and given / sent to the school to which they are applying . | XXX | ES Culham/ OSGES | Ongoing | Write a formal letter to the Director
4.D. Other issues regarding staff
Preparation of references |  |  | Generic reference for all staff. Staff can opt out if they wish. Specific reference on request. | XXX | ES Culham | Ongoing | Work in progress
Preparation of 'to do' list for staff in preparation for departure |  |  |  | XXX | ES Culham | Spring 2017 | Work in progress
Preparing settlement agreements and notice letters |  |  | Based on local legislation | XXX | ES Culham | Starting January 2017 | Work in progress
Termination of contracts of employment for locally recruited staff |  |  | Based on settlement agreement. Bursar consults with Head of HR when necessary | XXX | ES Culham/OSGES | 31/08/2017
5.Official letter/ certificate confirming the school closure Decision of the BoG with the signature of the Director . To be drawn up by OSGES. |  |  |  | XXX | ES Culham | In April 2017
6.Students
Storage of all student files including the files of students transferring to ESUK |  |  | To be kept ? Years - clarify. Files of students transferring to ESUK - needs to be clarified | XXX | ES Bergen | To be transported in summer 2017
The director of ES Bergen signs duplicates of BAC certificates if requested by former ES Culham students |  |  | Decision of the Board of Governors required. A document referring to the decision could be delivered to the students , together with the duplicates | XXX | OSGES/ ES Bergen | From 31/08/2017 | DONE
Transfer of pupil files to ESUK - hard copies |  |  | XXX has confirmed that a transfer of the personal data of students from the European School, Culham, to ESUK is legally possible provided that the students’ legal representatives have specifically agreed to it in writing. | XXX | ES Culham/ OSGES | summer 2017 | Clarify with ESUK which data they need. Work in progress
Transfer of electronic information on pupils to ESUK (SMS) |  |  | SMS issues to be clarified by the legal department. ESUK to clarify what data is required. Method of transfer to be clarified. Date of transfer to be clarified. | XXX | ES Culham/ OSGES/ ESUK | Summer 2017 | Clarify with ESUK which data will be needed. Need for a follow up from IT Unit. Does entry of end date in our school mean data will disappear?
BAC Issues
Scanning of 2017 BAC Scripts ES Culham does not need to buy the scanner for the digitization of the 2017 BAC scripts, ESUK will buy the scanner instead. ES Culham and ESUK staff will receive the necessary training at the same time. ESUK will lend ES Culham the scanner for the digitization of the 2017 BAC scripts. The scanner must be installed and set up in the administrative network of ES Culham. The scanning operations for the 2017 BAC will be performed by ES Culham staff. The scripts will only be handled by ES Culham staff For the 2018 session, the scanner will be set up in ESUK and staff will be retrained |  |  | Collaboration between ESC and ESUK | XXX | ES Culham / ESUK | December 2016 / January 2017 | Work in progress
Online correction 2017 BAC Scripts Teachers in ES Culham and ESUK will be trained at the same time for the 2017 EB session Examination scripts for the 2017 EB session will be corrected on-line by ES Culham teachers Examination scripts for the 2018 EB session will be corrected on-line by ESUK teachers. (There will be a retraining in 2018) |  |  | Collaboration between ESC and ESUK | XXX | ES Culham / ESUK | January / March 2017 | Work in progress
Storage of all BAC papers of the last 3 years |  |  | To be kept 3 years | XXX | ES Bergen | To be transported in July or August 2017
Storage of BAC artwork for three years in ESUK to facilitate collection by former students |  |  | Consult XXX - agreed | XXX | ESUK | To be handed over in July/August 2017
Facilitate smooth transfer of students with Intensive Support Contracts - early discussion of options with parents at Support Advisory Group meetings in January 2017; if ESUK the chosen option, invite ESUK SUPCO |  |  | Consult XXX - agreed | XXX | ESC / ESUK | 2017-01-01 | DONE
Admission to ES in Brussels - an extra line concerning Culham students in 2017 will be added to the admission document (Concerns also Cat 3 students) |  |  | See document 2016-10-D-21-en-1 | XXX | OSGES | Students apply during Phase 1 | DONE
Students wishing to finish their studies in another European School |  |  | See document 2016-10-D-21-en-1 | XXX | ES Culham/ OSGES | BOG December 2016 | DONE
UCAS references
UCAS dossiers of our current S6 to be transferred to ESUK following written requests from parents |  |  | Agreement letter needed from the parents | XXX | ES Culham/OSGES | 2017-07-01
UCAS references - after the closure. |  |  | Director of Bergen gets the request from the students who pay ES Bergen. XXX (possibly XXX) can be consultants but the references will be produced by ES Bergen. Payment from ES Bergen to the consultants. | XXX- agreed | ES Bergen | After August 2017 | It has been agreed that the necessary subject referencies will be produced by ESC and stored by ESBergen for pupils not applying to University this year.
7.Archives
Minutes of Admin. Board meetings |  |  | Uploaded on Learning Gateway | XXX | OSGES | End of August 2017 | Check!
Papers of Admin. Board meetings |  |  | Uploaded on Learning Gateway | XXX | OSGES | End of August 2017 | Check!
Storage of personal staff files |  |  | Stored in the archives of OSGES | XXX | OSGES | End of August 2017 | Agreed. Work in progress
Financial documents (salary files and records, accounting records) |  |  | Keep for 6 years; source: https://www.qualityformations.co.uk/resource-centre/keeping-records/ - where? | ? | OSGES | Autumn 2017/ July 2018
8. ICT
Admin computers to be cleaned. Hard drives to OSGES. XXX What about pedagogical PCs? Need to have certificates of data destruction |  |  | SLT meet with XXX to clarify; Keep important data e.g. about doublers to provide information in case of an appeal. | XXX | ES Culham/ OSGES | Before 31/08/2017. Limited number of computers operational last week of August to facilitate XXX final shutdown tasks | Needs consultation with ICT Unit. Enquiry sent to ESUK. 28 and 29 Aug - admin hard drives removed and final back-up.
Certificates of data destruction for all computers |  |  |  | XXX | ES Culham | Before 31/08/2017 | 150-200 computers in ped.network. The "cleaning machine" prints out the certificate. Buy the machine. ~300£ per machine.
PCs can then be donated to ESUK or to a charity. |  |  | First batch - October 2016 | XXX | ES Culham | Before 31/08/2017
Back-up for admin server |  |  | Done daily - automatically | XXX | ES Culham | Daily | 1 server
Back-up for teachers' files on the computers- should we back up and copy them ? |  |  | USB sticks to be provided end of April | XXX | ES Culham /OSGES | By 18/07/2017 | Consult with XXX whether we need back-up. Back-up by 18 July. Bitlocker!
The data in the user areas - again to be copied and backup made? |  |  | Check with XXX what is backed-up (AdminShared, etc) | XXX | ES Culham | Daily | Final back-up guidelines to be drawn by XXX
Staff to be informed about data transfer - need to clean computers. |  |  | Email accounts will remain open for 15 days after the end of the contract. Accounts will be left open for teachers transferred to other ES. Inform XXX about the staff whose accounts should be left open. | xxx | ES Culham/ OSGES | April 2017 | NB! Not esculham.net will not be open after the closure.
Adm server and devices to be returned to OSGES |  |  | XXX to inform XXX on procedures | XXX | To be sent to OSGES | Before 31/08/2017 | List on devices from OSGES
VPN (emails, SAP, PERSEE) access will be provided for Bursar after closure |  |  | Bursar has VPN connection, access to SMS etc, the same for Accountant. | XXX |  | In August 2017 | XXX will do that in the middle of August
VPN (emails, SAP, PERSEE) access will be provided for Accountant for a limited period |  |  | List of requirements | XXX |  | In August 2017
SMS to remain accessible for Bursar after closure |  |  | Inform XXX | XXX | ES Culham/ OSGES | At the beginning of 2017
SMS leaving date for pupils transferring to ESUK - 07/07/2017 or 31/08/2017 as the latest date |  |  |  | XXX | ES Culham/ OSGES | August 2017 | Check with ICT Unit! Will the data on SMS disappear after the end date will be entered
E-mail accounts for management |  |  | The accounts will beclosed 15 days after school closure. Need for a longer period | XXX | OSGES | 2017-09-01
General e-mail account for ES Culham after the closure |  |  | On school website; Accountant to deal with enquiries. | XXX | ES Culham/ OSGES | September 2017 -June 2018
E-mail accounts for pupils |  |  | Will be closed | XXX | ES Culham | Stopped on 22 August 2017 | To be closed on 22 August 2017
Close down school website - information redirected |  |  | Registered domain open- direct to ES website - managed by XXX | XXX | ES Culham | 2017-08-01
Termination of Microsoft licences |  |  | XXX to inform of procedure - teachers to be informed | XXX | OSGES | 2016/2017
9. Financial issues
Payments as of 1 September 2017
Sickness Fund as of 1 September 2017 |  |  | Members of staff apply personally to the Sickness Fund for a further 6 months or in case of serious illness; Invite somebody from the Sickness Fund here (Head of HR - to indicate the right person) to give the necessary information on procedures for extension of sickness fund or provide necessary information some other way. | XXX | ES Culham/ OSGES | Before the end of August final contribution.
Salary increase from 01.07.2017 payable in 2018 |  |  | Bursar makes the calculation; paid by OSGES
Other financial issues
Unpaid school fees written off by written procedure by the end of August 2017 |  |  | Written procedure | XXX | ES Culham | By the end of August 2017
To deal with tax calculation of seconded staff |  |  |  | XXX | OSGES | ASAP | Work in progress
Termination of Category 2 agreements |  |  |  | XXX | ES Culham | Notice to be given in January 2017 | DONE
Budget 2018 – Bursar’s salary and staff salary back payments for July and August 2017 |  |  | XXX prepares and forwards to XXX | XXX | ES Culham | In January 2017 | Budget for 2018 prepared
A letter to be sent concerning national salary slips for the teachers who will finish their secondments |  |  |  | XXX | ES Culham | May-June 2017
Payment of invoices after 31/08/2017 |  |  |  | XXX | ES Culham | After 31/08/2017
Collection of any unpaid school fees |  |  |  | XXX | ES Culham | After 31/08/2017
Access to SAP, SMS, PERSEE |  |  | To be solved via VPN connection | XXX | OSGES | In June 2017
Payment of resettlement and departure allowances |  |  | Seconded | XXX | ES Culham | Try to pay before 31/12/2017
Payment of removal expenses |  |  | Seconded + locally recruited teaching staff | XXX | ES Culham | Try to pay before 31/12/2017
Submission of national tax documents ( differential allowance) |  |  | Seconded - Bursar forwards outstanding cases in 2018 to OSGES | XXX | ES Culham
National salary slips submitted after 31/08/2017 |  |  | Seconded | XXX | ES Culham | After 31/08/2017
Close down the SAGE payroll |  |  | Payroll for locally recruited teachers and AAS | XXX | ES Culham | By the end of August 2017
Banking arrangements |  |  | Request for the bank account to be open after the closure. Document for the AdminBoard | XXX | ES Culham | 31/08/2017 | Still to be decided
Appointment of the Authorising officer |  |  | Deputy Secretary General | XXX | OSGES | Before August 2017
Issue of P45's to LR staff (teaching and AAS) |  |  |  | XXX | ES Culham | End of August 2017
Settlement Agreement payments |  |  |  | XXX | ES Culham | Will be paid 15 August 2017 with final salaries
Termination of contracts for goods and services |  |  | List to be drawn | XXX | ES Culham | To be done before 31/08/2017 | Work in progress
Termination of pension schemes |  |  |  | XXX | ES Culham | To be done before 31/08/2017
Termination of Joint Sickness Insurance Scheme ( seconded staff) |  |  | 6 months extension if can't get cover in home country |  |  | To be done before 31/08/2017
Disposal of old salary and accounting records |  |  | Check how long to be stored | XXX | OSGES | Work in progress
10. Buildings and equipment
Disposal of unwanted furniture and equipment |  |  |  | XXX | ES Culham | In summer 2017
Hand over keys to Europa School |  |  |  | XXX | ES Culham | In summer 2017
Disposal of unwanted files and papers |  |  | Confidential papers to be shredded | XXX | ES Culham | In progress
Disposal of unwanted materials and equipment in classrooms |  |  |  | XXX | ES Culham | In summer 2017
Disposal of chemicals |  |  | Dispose using a specialised company - consult XXX re. possible handover | XXX | ES Culham | In summer 2017 or earlier
Library - cancel magazine subscriptions |  |  |  | XXX | ES Culham | During 2017
Vacating of buildings |  |  | Discussed with representatives of DfE | XXX | ES Culham/DfE | 2017-08-31 | ESUK has to inform Dfe which areas they need earlier but only after 17 July 2017
11. Administrative arrangements
Cancelling X number plates for seconded staff |  |  |  | XXX | ES Culham | To be done before 31/08/2017 | Work in progress
Cancelling school registration with UK Foreign Office |  |  |  | XXX | ES Culham | To be done before 31/08/2017
Collection of keys from staff |  |  |  | XXX | ES Culham | Before staff leave
Dealing with mail received after 31/08/2017 |  |  | A pigeon hole for ES Culham in ESUK and mail to be collected by Bursar
On site storage facilities after 31/08/2017 |  |  | Temporary storage may be required for BAC art work, etc
Culham, March 2017
Note on I10: MARCHEGGIANO Giancarlo (OSG): it is not clear what happens to the file of a seconded teacher when he/she is transferred (and when he/she leaves the system?) Should we keep some files, we should discuss with Bxl1 the possibility to store them.